## Activities
Activity Name | Type | Week | Responsible | Estimated Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
Week 1
Learn Eclipse | Preparation | 1 |  |  |  | Done | Learning SVN, Eclipse well critical to project success
Role preferences | Coordination | 1 |  |  |  | Done
Learn SVN | Preparation | 1 |  |  |  | Delayed
Wiki setup | Preparation | 1 |  |  |  | Ongoing
Team formation | Preparation | 1 |  |  |  | Planned
Brainstorm project concept | Requirements | 1 |  |  |  | Planned
Project concept writeup | Documentation | 1 |  |  |  | Planned
Identify role owners | Preparation | 1 |  |  |  |  | Multiple roles are OK - think about role & reponsibility distribution
Team Roster | Documentation | 1
Weekly team meeting | Coordination | 1
Weekly report | Documentation | 1
Week 2
Repository setup | Preparation | 2
Define requirements | Requirements | 2
Create, share paper prototype | Requirements | 2
Requirements document | Requirements | 2
Update activity tracker | Documentation | 2
Create acceptance tests | Testing | 2
Choose processes | Coordination | 2
Update risk/issues on Wiki | Coordination | 2
Weekly team meeting | Coordination | 2
Weekly report | Documentation | 2
Week 3
Note on C1: swami: This is useful for generating subtotals and reports
Note on D1: SE: The person responsible for ensuring completion, not necessarily all the people doing it
Note on H1: swami: Insert your own comments
Note on I1: SE: This field is updated automatically

## Instructions
Using the activity plan
Fill in hours to be spent on each activity during each week
If 5 team members each will spend an hour, that counts as 5 hours
If you spend time on an activity not listed in the tracker, add the activity and list actual hours
For new activities, identify the type of activity - documentation, coordination, estimation etc.
Identify people responsible for each activity
Estimate the hours needed for the activity